**2022 FAMILY CAMPAIGN TIMELINE**

**Date Task Responsibility**

Due November 30, 2021 Recruit Family FOS Chair Finance Chairman

December 2, 2021 District FOS Briefing District Executive

November & December Recruit Unit FOS Presenters & Unit Coordinators Family Chairman

December - January Contact Units to Schedule FOS Presentations Family Chairman

January 15, 2022 All Unit FOS Presentations Scheduled Family Chairman

January 27, 2022 FOS Presenter Training/Practice District Executive

January 1 - May 30, 2022 Conduct Unit FOS Presentations Family Presenters

June 1, 2022 Conclusion of 2022 FOS Campaign Family Chairman

June - July Conduct Clean-Up Campaign (follow up calls) District Executive

June 2023 FOS Campaign Kickoff Recruiting & Planning Council FOS Chair